## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
sprint 1 | sprint 1 | US_01 | As a user, I want to enter a target domain/IP to scan | MUST HAVE | Nmap Installed | sumanjali | 3- Completed
sprint 1 | sprint 1 | US_01 | As a system, I want to scan top 1000 ports using Nmap | MUST HAVE | Nmap Installed | sumanjali | 3- Completed
sprint1 | sprint 1 | US_01 | As a system, I want to extract port, service, version details | MUST HAVE | Scanner Module | sumanjali | 3- Completed
sprint2 | sprint2 | US_01 | As a system, I want to integrate VirusTotal API for threat data | MUST HAVE | API Key | sumanjali | 3- Completed
sprint2 | sprint2 | US_01 | As a system, I want to normalize VT data for analysis | MUST HAVE | VT Data | sumanjali | 3- Completed
sprint2 | sprint2 | US_01 | As a system, I want to calculate exposure score based on ports | MUST HAVE | Analyzer | sumanjali | 3- Completed
sprint3 | sprint3 | US_01 | As a system, I want to calculate threat score from VT data | MUST HAVE | Analyzer | sumanjali | 3- Completed
sprint3 | sprint3 | US_01 | As a system, I want to compute overall risk score and severity | MUST HAVE | Analyzer | sumanjali | 3- Completed
sprint3 | sprint3 | US_01 | As a user, I want recommendations based on detected services | MUST HAVE | Streamlit | sumanjali | 3- Completed
sprint4 | sprint4 | US_01 | As a user, I want a dashboard with charts and metrics | MUST HAVE | Plotly | sumanjali | 3- Completed
sprint4 | sprint4 | US_01 | As a user, I want pie and bar charts for risk visualization | SHOULD HAVE | Plotly | sumanjali | 3- Completed
sprint4 | sprint4 | US_01 | As a user, I want heatmap visualization of risk scores | SHOULD HAVE | Database | sumanjali | 3- Completed
sprint5 | sprint5 | US_01 | As a user, I want historical scan tracking | SHOULD HAVE | Database | sumanjali | 3- Completed
sprint5 | sprint5 | US_01 | As a user, I want trend analysis across scans | SHOULD HAVE | Database | sumanjali | 3- Completed
sprint5 | sprint5 | US_01 | As a user, I want email alerts for critical vulnerabilities | COULD HAVE | SMTP setup | sumanjali | 3- Completed
sprint6 | sprint6 | US_01 | As a user, I want heatmap visualization of risk scores | COULD HAVE | Plotly | sumanjali | 3- Completed
sprint6 | sprint6 | US_01 | As a user, I want PDF report generation | COULD HAVE | FPDF | sumanjali | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7